## Sheet1
| Test Planner and Tracker |  |  | Team Number - 12 | Akshat Goyal, Kanish Anand, Nikunj Nawal and Sridhar M
S.No | Planned Sprint No. | Related Use case | Pre-conditions | Test Description (steps) | Expected Outcome | Sprint 2 | Comments | Sprint 3 | Comments | Sprint 4 | Comments | R1 | Comments | Sprint 5 | Comments | Sprint 6 | Comments | Sprint 7 | Comments | Sprint 8 | Comments | R2 | Comments
1 | 3 | View predicted values for energy consumption on Jupyter notebook | data is required. data cleaning, model to be selected, feature engineering | Plot graph of predicted values for the entire year | graph should be similar to the graph produced by original data | NA |  |  | not enough data was provided to work on
2 | 3 | View energy consumption graph of data provided on Jupyter notebook | data is required. data cleaning, model to be selected, feature engineering | The output should correspond to the given data | The output should correspond to the given data | NA |  |  | not enough data was provided to work on
3 | 4 | Login and Register for different roles for the system | types of users should be defined, functional UI should be available | Try registering multiple times using the same user name. Login with different combinations of inputs | get error while registering or logingin | NA |  | NA
4 | 5 | View predicted value for energy consumption | data is required. data cleaning, model to be selected, feature engineering | Plot graph of predicted values for the entire year | graph should be similar to the graph produced by original data | NA |  | NA |  | NA |  | NA
5 | 5 | Get help regarding the web-app | Functional email sending options/ information should be available | User should be able to contact the maintainer/developer | contact mail sent | NA |  | NA |  | NA |  | NA |  |  | Delay due to corona outbreak
6 | 5 | Give user feedback via the web-app | Functional email sending options/ information should be available, feedback form should be available | Feedback form should save the input and mail to the help person | feedback should be recieved | NA |  | NA |  | NA |  | NA |  |  | Delay due to corona outbreak
7 | 5 | View graphical analysis of energy consumption | data is required. data cleaning, model to be selected, feature engineering, graphs to be selected | Verify output via graph generator API call using code | graph should be similar to the graph produced by original data | NA |  | NA |  | NA |  | NA |  |  | Delay due to corona outbreak
8 | 6 | Download the generated energy consumption prediction graphs | graphs should be generated, data should be available | Verify using the web technology already available in browsers | data should be downloaded | NA |  | NA |  | NA |  | NA |  | NA
9 | 6 | Download the given energy consumption data in form of graphs | graphs should be generated, data should be available | Verify using the web technology already available in browsers | data should be downloaded | NA |  | NA |  | NA |  | NA |  | NA
10 | 6 | Download the generated budget prediction graphs | graphs should be generated, data should be available | Verify using the web technology already available in browsers | data should be downloaded | NA |  | NA |  | NA |  | NA |  | NA
11 | 7 | View budget Prediction | Funtional UI frame should be available, range selection buttons should function, data should be available, energy to currency conversation in formation should be available | Run code to calculate the budget of actual data and verify it by passing the data in our system | data should be equal |  |  | NA |  | NA |  | NA |  | NA |  | NA |  |  | Rate APIs were not available |  | Decided to leave after consulting with client |  | Decided to leave after consulting with client
12 | 7 | View notification for an anomaly | email shoud be given/updated, anomaly fuction should be decided, data should be available | Manually check the notification for the forged anomalous data | notification should be visible | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  |  | Anomaly fuction not confirmed
13 | 7 | View actual data of energy consumption | data is required. Data fectching mechanism to be developed | Total consumption in given data should match the output checked via google spreadsheet API call using code | values shoud match | NA |  | NA |  | NA |  | NA |  | NA |  | NA
14 | 7 | View current energy consumption | Continuous updates should be available for consumption data fetching | Total consumption in given data should match the data obtained | values shoud match | NA |  | NA |  | NA |  | NA |  | NA |  | NA
15 | 7 | Check the total consumption of energy | data should be available | Total consumption in given data should match the data obtained | values shoud match | NA |  | NA |  | NA |  | NA |  | NA |  | NA
16 | 7 | Update profile of the logged-in user | User should log in, types of users to be finalized, backend should be functional to save data | Updating profile should update values in the backend data | able to see values in backend | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  |  | Profile section to be redesigned
17 | 7 | Update the email for receiving the anomalous data updates | email should be given/updated, anomaly function should be decided, data should be available | Updating email should update the value in the backend data | able to see values in backend | NA |  | NA |  | NA |  | NA |  | NA |  | NA
18 | 8 | View weather forecast | finalize APIs to be used, functional UI frame should be available | Run the test API and also verify with open-weather site | Same value to be obtained | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA
19 | 8 | View anomaly cases as a list | anomaly fuction should be decided, data should be available. functional UI should be available | Total consumption in given data should match the data obtained | values shoud match | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA
20 | 8 | Select API for weather forecast | Finalize APIs to be used, functional UI frame should be available | Selecting API should give value corresponding to their site | Corresponding values to be obtained | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA